## Sheet1
CSI4142 - Project 2023
Phase 3- OLAP and BI Dashboard
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
OLAP queries
Drill down, roll up | Alex De Furia | 2024-04-03 | 2024-04-03 | 0.5 | 0.5
Slice | Alex De Furia | 2024-04-03 | 2024-04-03 | 0.5 | 0.5
Dice | Alex De Furia | 2024-04-03 | 2024-04-03 | 0.5 | 0.5
Composite OLAP - 4 queries | Jacob Kszan | 2024-04-03 | 2024-04-05 | 0.5 | 2
Icebergs | Jacob Kszan | 2024-04-03 | 2024-04-03 | 0.5 | 0.5
Windowing - partition | Malte Blomqvist | 2024-04-03 | 2024-04-03 | 0.5 | 0.5
Window | Malte Blomqvist | 2024-04-03 | 2024-04-04 | 0.5 | 1
BI dashboard
Design of data mart | Jacob Kszan | 2024-04-03 | 2024-04-03 | 2 | 2
Importing data | Jacob Kszan | 2024-04-03 | 2024-04-03 | 0.5 | 0.5
OLAP queries | Malte Blomqvist | 2024-04-03 | 2024-04-04 | 4 | 4
Figures | Malte Blomqvist | 2024-04-03 | 2024-04-05 | 4 | 4
Other tasks - please specify