## Phase3-TeamPlanning2023
CSI4142 - Project 2023
Phase 4 - Data Mining
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing | [5 empty] | Alexander De Furia was responsible for the bulk of this phase of the project as agreed upon previously as Malte and Jake took a greater role in Phase 3. All group members were consulted during Phase 4 for approval and due dilligence. All group members completed an equal amount of work throughout the course of the project.
Data summarisation | Alexander De Furia | 1969-12-31 19:01 | 1969-12-31 19:01 | 1 | 1
.. Visualisation of attributes | Alexander De Furia | 1969-12-31 19:01 | 1969-12-31 19:01 | 1 | 2
Data transformation | Alexander De Furia | 1969-12-31 19:01 | 1969-12-31 19:01 | 2 | 3
.. Missing values | Alexander De Furia | 1969-12-31 19:01 | 1969-12-31 19:01 | 0 | 0
.. Categorical data | Alexander De Furia | 1969-12-31 19:01 | 1969-12-31 19:01 | 0 | 0
.. Numeric data | Alexander De Furia | 1969-12-31 19:01 | 1969-12-31 19:01 | 0 | 1
.. Feature selection | Alexander De Furia | 1969-12-31 19:01 | 1969-12-31 19:01 | 2 | 2
Data mining - Classification | NA
Decision tree | NA
Gradient Boosting | NA
Random Forests | NA
Comparison of results | NA
Summary | NA
Anomaly detection
One-class SVM | Alexander De Furia | 1969-12-31 19:01 | 1969-12-31 19:01 | 2 | 3
DBSCAN | Alexander De Furia | 1969-12-31 19:01 | 1969-12-31 19:01 | 2 | 1
Summary | Alexander De Furia | 1969-12-31 19:01 | 1969-12-31 19:01 | 1 | 3
Other tasks - please specify