## Phase3-TeamPlanning2023
CSI4142 - Project 2023
Phase 4 - Data Mining
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing
Data Aggregations | Jacob Kszan | 2024-04-06 | 2024-04-07 | 1 | 1
Visualisations | Malte Blomqvist | 2024-04-07 | 2024-04-07 | 1 | 2
Data transformations | Malte Blomqvist | 2024-04-06 | 2024-04-06 | 2 | 3
Dealing with Missing values | Jacob Kszan | 2024-04-07 | 2024-04-07 | 1 | 2
Feature selection | Alexander De Furia | 2024-04-08 | 2024-04-08 | 2 | 2
Data mining - Classification | NA
Decision tree | NA
Gradient Boosting | NA
Random Forests | NA
Comparison of results | NA
Summary | NA
Anomaly detection
One-class SVM | Alexander De Furia | 2024-04-08 | 2024-04-08 | 2 | 3
DBSCAN | Alexander De Furia | 2024-04-08 | 2024-04-08 | 2 | 1
Summary | Alexander De Furia | 2024-04-08 | 2024-04-08 | 1 | 3
Other tasks - please specify