## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties |  | Alex: Data Staging, Parsing, and Validation |  | Malte: Data Staging, Preprocessing, and Nearest Neighbour
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database Docker image instance / initialization pipeline | Jacob Kszan | 13/03/2024 | 12/03/2024 | 2 | 1.5
Adjusting SQL schema to include lookup tables | Jacob Kszan | 22/03/2024 | 22/03/2024 | 1 | 1
Writing/organizing the surrogate key generation pipeline | Jacob Kszan | 22/03/2024 | 21/03/2024 | 1 | 2
Loading SQL schema into the Docker image | Jacob Kszan | 14/03/2024 | 13/03/2024 | 1.5 | 1
Creating preprocessing script for hotspot (Fire) data | Malte Blomqvist, Alex De Furia | 22/03/2024 | 20/03/2024 | 6 | 16
Creating preprocessing script for yearly land cost | Malte Blomqvist | 22/03/2024 | 21/03/2024 | 0.5 | 0.5
Calculating Inflation across years for yearly land cost | Malte Blomqvist | 22/03/2024 | 20/03/2024 | 0.5 | 0.5
Creating nearest neighbour script(s) to link fires to their nearest weather stations | Malte Blomqvist, Alex De Furia | 22/03/2024 | 26/03/2024 | 7 | 18 | This was much more difficult than anticipated due to issues with the weather API
Staging of fact table | Jacob Kszan | 22/03/2024 | 25/03/2024 | 2.5 | 2
Creating Data Staging Scripts | Alex De Furia and Jacob Kszan | 22/03/2024 | 24/03/2024 | 10 | 15
Automating injestion of produced CSV data files into SQL | Alex De Furia | 22/03/2024 | 23/03/2024 | 2 | 3 | Had to change schema slightly and create additional lookup tables to avoid using operational keys as primary keys
Parsing / Validating Firedata CSVs | Alex De Furia
Parsing / Validating Land Cost CSVs | Alex De Furia
Troubleshooting/Bugfixing the SQL schema | Jacob Kszan | 22/03/2024 | 23/03/2024 | 1 | 3
Troubleshooting/Bugfixing the NN algorithm | Malte Blomqvist, Alex De Furia | 22/03/2024 | 26/03/2024 | 2 | 6
Troubleshooting/Bugfixing the staging scripts | Malte Blomqvist, Alex De Furia, Jacob Kszan | 22/03/2024 | 26/03/2024 | 2 | 8 | Rewrote the staging scripts to move from a direct SQL injection to a CSV-based approach
Discussing SQL Schema Redesign and Solving API Access Issues | Malte Blomqvist, Alex De Furia, Jacob Kszan | 22/03/2024 | 26/03/2024 | 4 | 4